## ReadMe
ISO 31000 Third-Party Risk Assessment
Self-directed learning project
WHY I BUILT THIS
I built this to practice the ISO 31000 risk process on a realistic vendor scenario while studying for CRISC and working through ISO 31000 concepts. It's not client or employer work, I used a fictional bank and vendor so I could work through the full cycle (context, identification, analysis, evaluation, treatment, monitoring) the way I would want to on the job, and see how it connects to the ISO 27001 controls which I already know from my Lead Implementer training.
A NOTE ON SCOPE AND EXPERIENCE
I set the scenario at an APRA regulated bank and a cloud vendor because that's the kind of environment CPS 230 and Material Service Provider obligations actually apply to, and I wanted to learn the terminology properly. In a real organisation this work is normally split across a risk team, not done individually, so treat this as my working method, not a claim of having run a program like this end to end for a real client.
Assessing organisation: Meridian Financial Group (fictional). Third party assessed: CloudVault Data Services (fictional), a Material Service Provider hosting and backing up core banking data.
HOW TO READ THIS WORKBOOK
Context & Criteria : scope, risk appetite, and the likelihood/impact scales used throughout.
Risk Register : the full identify > analyse > evaluate > treat cycle for six illustrative risks.
Heat Map : inherent vs residual risk plotted on a 5x5 matrix, plus a summary chart.
Monitoring & KRIs : the ongoing review cadence and indicators used to track this vendor.
ISO 31000-27001 Crosswalk : maps each ISO 31000 stage to the ISO 27001 clause/control it satisfies.
KEY
Blue text = an input cell (edit this to reuse the template for a different vendor).
Black text = a formula (recalculates automatically, do not overwrite).
Blue text = input cell
Black text = formula
NOTE
This is a learning artefact, built to show how I think through a risk problem, not a finished consulting deliverable. If you ask me about it in an interview, I'm happy to walk through why I scored each risk the way I did and what I'd still want to learn before doing this for real.

## Context & Criteria
Establishing the Context
Assessing organisation | Meridian Financial Group (illustrative APRA-regulated ADI)
Third party assessed | CloudVault Data Services (illustrative Material Service Provider)
Engagement scope | Cloud hosting and backup of core banking data, including disaster recovery services
Internal context | ISO 27001-certified ISMS in operation; existing Material Service Provider register identifies this vendor as high-criticality due to core banking data access
External context | APRA CPS 230 (fully enforceable 1 July 2026); Privacy Act 1988; rising ransomware targeting of managed service providers across the sector
Risk appetite statement | Meridian has low tolerance for risks that could expose customer data or interrupt core banking availability beyond a 4-hour recovery time objective. Risks scoring Extreme cannot be accepted without Board Risk Committee sign-off.
Assessment date | 15 September 2026 (illustrative)
Next scheduled review | 15 September 2027, or earlier if triggered (see Monitoring & KRIs)
Likelihood Scale
Rating | Description
1 | Rare — may occur only in exceptional circumstances
2 | Unlikely — could occur at some point, but not expected
3 | Possible — might occur during the life of this engagement
4 | Likely — will probably occur at least once during this engagement
5 | Almost certain — expected to occur, or evidence shows it already has
Impact Scale
Rating | Description
1 | Insignificant — no material effect on data, service, or compliance
2 | Minor — brief internal inconvenience, no customer or regulator impact
3 | Moderate — limited customer impact or a contained compliance gap
4 | Major — customer data or service availability affected; regulator notification likely
5 | Severe — large-scale data exposure, extended outage, or breach of a CPS 230 obligation
Risk Level Bands (Likelihood x Impact)
Score Range | Risk Level
1 - 4 | Low
5 - 9 | Medium
10 - 14 | High
15 - 25 | Extreme

## Risk Register
Risk ID | Category | Risk Description | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Score | Inherent Level | Treatment Option | Treatment Action | Owner | Target Date / Status | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Score | Residual Level
R1 | Data Security & Access Control | Unauthorised access to customer data due to inadequate access controls at CloudVault (no MFA enforced, access reviews not evidenced). | 3 | 5 | 15 | Extreme | Reduce | Require CloudVault to enforce MFA for all administrative access and conduct quarterly access reviews; Meridian to audit evidence annually. | IT Security Lead, Meridian | 31 Dec 2026 - In Progress | 2 | 5 | 10 | High
R2 | Operational Resilience | Extended service outage affecting core banking data backup availability, delaying restoration beyond Meridian's 4-hour RTO. | 2 | 4 | 8 | Medium | Reduce | Renegotiate SLA to a contractual 4-hour RTO / 1-hour RPO; require quarterly DR test evidence from CloudVault. | Vendor Relationship Manager | 31 Jan 2027 - In Progress | 1 | 4 | 4 | Low
R3 | Fourth-Party / Subcontracting | CloudVault subcontracts data processing to an offshore fourth party without Meridian's knowledge or approval (concentration and visibility risk). | 4 | 4 | 16 | Extreme | Reduce | Amend contract to require disclosure and prior approval of all subcontractors, with right to assess each fourth party's security posture. | Third-Party Risk Manager | 30 Nov 2026 - In Progress | 2 | 4 | 8 | Medium
R4 | Regulatory & Compliance | A data breach at CloudVault is not contractually required to be reported to Meridian within a defined timeframe, risking a missed CPS 230 / Privacy Act notification obligation. | 2 | 5 | 10 | High | Reduce | Mandate contractual notification to Meridian within 24 hours of any confirmed or suspected security incident. | Legal & Contracts | 31 Dec 2026 - In Progress | 2 | 5 | 10 | High
R5 | Business Continuity | CloudVault's business continuity and disaster recovery plan has never been tested, risking prolonged recovery in an actual disaster scenario. | 3 | 4 | 12 | High | Reduce | Require an annual, evidenced DR/BCP test with results shared with Meridian's Business Continuity Manager. | Business Continuity Manager | 28 Feb 2027 - In Progress | 2 | 4 | 8 | Medium
R6 | Contractual / Governance | The current service agreement contains no right-to-audit clause, limiting Meridian's ability to independently verify CloudVault's control environment. | 4 | 2 | 8 | Medium | Reduce | Add a right-to-audit clause to the contract, exercisable annually or following a material incident. | Legal & Contracts | 15 Sep 2026 - Closed | 1 | 2 | 2 | Low

## Heat Map
Inherent Risk Heat Map
| Likelihood -> | 1 | 2 | 3 | 4 | 5
5 |  | 0 | 1 | 1 | 0 | 0
4 |  | 0 | 1 | 1 | 1 | 0
3 |  | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 1 | 0
1 |  | 0 | 0 | 0 | 0 | 0
Impact
Residual Risk Heat Map
| Likelihood -> | 1 | 2 | 3 | 4 | 5
5 |  | 0 | 2 | 0 | 0 | 0
4 |  | 1 | 2 | 0 | 0 | 0
3 |  | 0 | 0 | 0 | 0 | 0
2 |  | 1 | 0 | 0 | 0 | 0
1 |  | 0 | 0 | 0 | 0 | 0
Impact
Risk Count by Level
Level | Inherent | Residual
Low | 0 | 2
Medium | 2 | 2
High | 2 | 2
Extreme | 2 | 0

## Monitoring & KRIs
Ongoing Monitoring & Review
Frequency | Activity | Owner
Quarterly | Vendor performance review | Third-Party Risk Manager
Annual | Full ISO 31000 risk reassessment | Risk Committee
Ad hoc | Triggered by: security incident, material contract change, adverse audit finding, or new regulatory guidance (e.g. updated CPS 230 guidance) | Third-Party Risk Manager
Annual | Reported to Board Risk Committee alongside the Material Service Provider register | CRO / Board Risk Committee
Key Risk Indicators (KRIs)
KRI | Linked Risk | Target | Current (illustrative) | Frequency | Trend
% of vendor access reviews completed on schedule | R1 | >=95% | 88% | Quarterly | Improving
SLA breaches affecting availability | R2 | 0 per quarter | 1 this quarter | Quarterly | Stable
Undisclosed fourth-party subcontractors identified | R3 | 0 | 1 (offshore processor) | Ongoing | Under remediation
Contractual breach-notification SLA in place | R4 | Yes, <=24 hrs | Not yet contracted | Per incident | Pending contract amendment
Evidenced DR/BCP test completed | R5 | Annual | Not yet tested | Annual | Scheduled Q1 2027

## ISO 31000-27001 Crosswalk
Where This Risk Assessment Feeds ISO 27001
ISO 31000 is the generic parent standard for risk management; ISO 27001's own risk process (Clause 6.1.2/6.1.3) is a domain-specific application of the same principles to information security. This tab shows how each stage of this project also satisfies an ISO 27001 requirement.
ISO 31000 Stage | What This Project Did | ISO 27001:2022 Clause | Relevant Annex A Controls | Linkage
Establishing the context | Defined scope, risk appetite, and likelihood/impact criteria for the CloudVault engagement | Clause 4.1/4.2, 6.1.2(a) | A.5.1 Policies for information security | ISO 27001 requires documented risk criteria before any assessment begins; the Context tab is that evidence.
Risk identification | Identified six risks tied to CloudVault's role as a Material Service Provider | Clause 6.1.2(c) | A.5.9 Inventory of assets, A.5.19 Information security in supplier relationships | Supplier risk identification under A.5.19 starts from exactly this kind of register.
Risk analysis & evaluation | Scored each risk (likelihood x impact) and compared it against Meridian's risk appetite | Clause 6.1.2(d)/(e) | Feeds the Statement of Applicability (SoA) | The scored register is the evidence an auditor expects behind SoA justification for supplier controls.
Risk treatment | Defined a treatment action, owner, and target date for each risk (MFA, audit rights, DR testing, subcontractor disclosure) | Clause 6.1.3, 8.3 | A.5.20 Supplier agreements, A.5.21 ICT supply chain, A.5.22 Monitoring supplier services | Each treatment action maps to a specific Annex A control, this is where the register becomes audit evidence.
Monitoring & review | Set a quarterly/annual review cadence and five KRIs to track this vendor on an ongoing basis | Clause 9.1, 9.3 | A.5.35 Independent review, A.5.36 Compliance with policies and standards | The KRI tab operationalises the continual monitoring Clause 9.1 requires but doesn't prescribe how to do.
Recording, reporting & consultation | Reported results to the Risk Committee quarterly and the Board annually | Clause 5.3, 7.4, 9.2 | Supports internal audit evidence trail | This is also the board-reporting evidence CPS 230 requires directly, one artefact serving two frameworks.